## Sheet1
S No | Task Description | Application | Web Page Name | Status | Priority | Estimate Start Date | Estimate End Date | Remarks
ADMIN SITE
1 | Pre-set Appointment | Admin Site | Appointment center | In Progress | 1 | 2021-10-08 | 2021-10-18 | Working on implementing the changes - 15% done
2 | Child Daily Information | Admin Site | Child Information | In Progress | 1 | 2021-10-18 | 2021-10-22 | These includes menu, allergy details also. Hence needs some time
3 | List of notifications | Admin Site | Notifications | Not Started | 1 | 2021-10-21 | 2021-10-27
4 | Compose notification changes | Admin Site | Notifications | Not Started | 1 | 2021-10-21 | 2021-10-27
5 | Broadcast notifification | Admin Site | Notifications | Not Started | 1 | 2021-10-21 | 2021-10-27
6 | Need to provide option to enter details and photo edit menu | Admin Site | Menu of the Year | Not Started | 2 | 2021-10-19 | 2021-10-29
7 | Need to provide option to enter details and photo add or edit the food | Admin Site | Food section | Not Started | 2 | 2021-10-19 | 2021-11-02
8 | Allergy and other details of the child | Admin Site | Child Information | In Progress | 2 | 2021-10-19 | 2021-11-02
9 | Change the landing view to calendar with all appointments available for that month, then provide options for teacher/children and new appointment and preset-appointment | Admin Site | Appointment center | In Progress | 2 | 2021-10-27 | 2021-10-29 | Need to implement changes as per pre-set appointment
10 | Booked/ checkout - status changes | Admin Site | Exchange Library | In Progress | 2 | 2021-11-01 | 2021-11-02
11 | Filter Child by allergy, privacy rights | Admin Site | Child Information | Not Started | 2 | 2021-11-02 | 2021-11-03
12 | Add Siblings to a child | Admin Site | Child Information | In Progress | 2 | 2021-11-03 | 2021-11-05
13 | Make privacy rights, nationality and classnames editable | Admin Site | Child Information | Not Started | 2 | 2021-11-08 | 2021-11-08
14 | Add classnames and users filters | Admin Site | School Documents | In Progress | 3 | 2021-11-09 | 2021-11-10 | Need to implement new design for the page
15 | Max size error for new document upload | Admin Site | School Documents | Not Started | 3 | 2021-11-09 | 2021-11-09
16 | Add options to view and download for documents | Admin Site | School Documents | Not Started | 3 | 2021-11-11 | 2021-11-11
17 | Need to provide option to show classname selection for new document | Admin Site | School Documents | In Progress | 3 | 2021-11-12 | 2021-11-12 | Need to implement new design for the page
18 | Option to select classname | Admin Site | Photo section | Completed | 3
19 | Option to add, delete and download | Admin Site | Photo section | In Progress | 3 | 2021-11-15 | 2021-11-16
20 | Main page - only title and onClick of title take to details page & edit/delete buttons | Admin Site | Mini club | Not Started | 4 | 2021-11-16 | 2021-11-21
21 | Edit and Add options | Admin Site | Marketing | Not Started | 4 | 2021-11-21 | 2021-11-25
PARENT APPLICATION
22 | Child profile information | Parent Application | My Profile | In Progress | 1 | 2021-10-08 | 2021-10-12 | Making changes to make the application dynamic
23 | Child Daily Information | Parent Application | Child Information | In Progress | 1 | 2021-10-14 | 2021-10-20 | Making changes to make the application dynamic
24 | Photos | Parent Application | Photos | In Progress | 2 |  |  | Making changes to make the application dynamic
25 | Message center | Parent Application | Messages | In Progress | 1 | 2021-10-21 | 2021-10-22 | Making changes to make the application dynamic
26 | Appointment center | Parent Application | Appointment | In Progress | 1 | 2021-10-25 | 2021-10-28 | Making changes to make the application dynamic
27 | School Documents | Parent Application | School Documents | In Progress | 2 | 2021-10-28 | 2021-10-29 | Making changes to make the application dynamic
28 | Exchange Library | Parent Application | Exchange Library | In Progress | 2 | 2021-10-29 | 2021-11-02 | Making changes to make the application dynamic
29 | Mini Club | Parent Application | Mini club | Not Started | 3 | 2021-11-16 | 2021-11-21
COMPLETED
30 | Add new Classname | Admin Site |  | Completed
31 | Users page changes | Admin Site | Teachers & Admins | Completed
32 | Users page - details view & edit/delete options | Admin Site | Teachers & Admins | Completed
33 | Sorting the users and childern in Alphabetic order | Admin Site |  | Completed
34 | Show all children at one place and able to select as per classname filter | Admin Site | Child Information | Completed
35 | Children details edit ( only for admin role) | Admin Site | Child Information | Completed
36 | New Child changes - mutliple nationalities and other.. | Admin Site | Child Information | Completed
37 | Delete message | Admin Site | Message Center | Completed
38 | Sending photos in message | Admin Site | Message Center | Completed
39 | Add privacy and other rights | Admin Site | Child Information | Completed
40 | Changes for Add book | Admin Site | Exchange Library | Completed
41 | Main page - only title and onClick of title take to details page & edit/delete buttons | Admin Site | Exchange Library | Completed
42 | Search by bookname, authorname and code | Admin Site | Exchange Library | Completed
43 | Donated by to be added for new book | Admin Site | Exchange Library | Completed