## Sheet1
S No | Application | Web Page Name | Task Description | Status | Priority | Estimate Start Date | Estimate End Date | Remarks
ADMIN SITE
1 | Admin Site | Appointment center | Pre-set Appointment | In Progress | 1 | 2021-10-08 | 2021-10-18 | Working on implementing the changes - 15% done
2 | Admin Site | Child Information | Child Daily Information | In Progress | 1 | 2021-10-18 | 2021-10-22 | These includes menu, allergy details also. Hence needs some time
3 | Admin Site | Notifications | List of notifications | Not Started | 1 | 2021-10-21 | 2021-10-27
4 | Admin Site | Notifications | Compose notification changes | Not Started | 1 | 2021-10-21 | 2021-10-27
5 | Admin Site | Notifications | Broadcast notifification | Not Started | 1 | 2021-10-21 | 2021-10-27
6 | Admin Site | Menu of the Year | Need to provide option to enter details & photo edit menu | Not Started | 2 | 2021-10-19 | 2021-10-29
7 | Admin Site | Food section | Need to provide option to enter details & photo add/edit food | Not Started | 2 | 2021-10-19 | 2021-11-02
8 | Admin Site | Child Information | Allergy & other details of the child | In Progress | 2 | 2021-10-19 | 2021-11-02
9 | Admin Site | Appointment center | Change the landing view to calendar with all appointments available for that month, provide options for teacher/children & new appointment & preset-appointment | In Progress | 2 | 2021-10-27 | 2021-10-29 | Yasmeen's notes: it is completed. Just need to implement changes as per pre-set appointment
10 | Admin Site | Exchange Library | Booked/checkout - status changes | In Progress | 2 | 2021-11-01 | 2021-11-02
11 | Admin Site | Child Information | Filter Child by allergy, privacy rights | Not Started | 2 | 2021-11-02 | 2021-11-03
12 | Admin Site | Child Information | Add Siblings to a child | In Progress | 2 | 2021-11-03 | 2021-11-05 | Yasmeen's notes:It is completed. Just glitches with nationality.. To fix
13 | Admin Site | Child Information | Make privacy rights, nationality & classnames editable | Not Started | 2 | 2021-11-08 | 2021-11-08
14 | Admin Site | School Documents | Add classnames & users filters | In Progress | 3 | 2021-11-09 | 2021-11-10 | Yasmeen's Notes: its working, just Need to implement new design for the page
15 | Admin Site | School Documents | Max size error for new document upload | Not Started | 3 | 2021-11-09 | 2021-11-09
16 | Admin Site | School Documents | Add options to view & download for documents | Not Started | 3 | 2021-11-11 | 2021-11-11
17 | Admin Site | School Documents | Need to provide option to show classname selection for new document | In Progress | 3 | 2021-11-12 | 2021-11-12 | Yasmeen's notes: Just need to implement new design for the page
19 | Admin Site | Photo section | Option to add, delete and download | In Progress | 3 | 2021-11-15 | 2021-11-16
20 | Admin Site | Mini club | Same lay out as exchange library | Not Started | 4 | 2021-11-16 | 2021-11-21
21 | Admin Site | Marketing | Edit and Add options | Not Started | 4 | 2021-11-21 | 2021-11-25
PARENT APPLICATION
22 | Parent Application | My Profile | Child profile information | In Progress | 1 | 2021-10-08 | 2021-10-12 | Making changes to make the application dynamic
23 | Parent Application | Child Information | Child Daily Information | In Progress | 1 | 2021-10-14 | 2021-10-20 | Making changes to make the application dynamic
24 | Parent Application | Photos | Photos | In Progress | 2 |  |  | Making changes to make the application dynamic
25 | Parent Application | Messages | Message center | In Progress | 1 | 2021-10-21 | 2021-10-22 | Making changes to make the application dynamic
26 | Parent Application | Appointment | Appointment center | In Progress | 1 | 2021-10-25 | 2021-10-28 | Making changes to make the application dynamic
27 | Parent Application | School Documents | School Documents | In Progress | 2 | 2021-10-28 | 2021-10-29 | Making changes to make the application dynamic
28 | Parent Application | Exchange Library | Exchange Library | In Progress | 2 | 2021-10-29 | 2021-11-02 | Making changes to make the application dynamic
29 | Parent Application | Mini club | Mini Club | Not Started | 3 | 2021-11-16 | 2021-11-21
TEACHERS SITE
COMPLETED
18 | Admin Site | Photo section | Option to select classname | Completed | 3
30 | Admin Site |  | Add new Classname | Completed
31 | Admin Site | Teachers & Admins | Users page changes | Completed
32 | Admin Site | Teachers & Admins | Users page - details view & edit/delete options | Completed
33 | Admin Site |  | Sorting the users and childern in Alphabetic order | Completed
34 | Admin Site | Child Information | Show all children at one place and able to select as per classname filter | Completed
35 | Admin Site | Child Information | Children details edit ( only for admin role) | Completed
36 | Admin Site | Child Information | New Child changes - mutliple nationalities and other.. | Completed
37 | Admin Site | Message Center | Delete message | Completed
38 | Admin Site | Message Center | Sending photos in message | Completed
39 | Admin Site | Child Information | Add privacy and other rights | Completed
40 | Admin Site | Exchange Library | Changes for Add book | Completed
41 | Admin Site | Exchange Library | Main page - only title and onClick of title take to details page & edit/delete buttons | Completed
42 | Admin Site | Exchange Library | Search by bookname, authorname and code | Completed
43 | Admin Site | Exchange Library | Donated by to be added for new book | Completed